# TerraGlow Skincare: Risk Mitigation Strategy

This document outlines the potential risks associated with the launch and operation of TerraGlow Skincare, along with specific, actionable mitigation strategies to ensure project success.

# 1. Supply Chain & Packaging Risks

## Risk: Zero-Waste Packaging Delays or Shortages

Because TerraGlow relies exclusively on 100% recyclable, zero-waste packaging, any disruption with the primary supplier could halt production or force the brand to compromise its core sustainability values.

### Mitigation:

Identify and vet at least two secondary eco-friendly packaging suppliers during Phase 2 (Sourcing). Negotiate backup contracts and maintain a buffer stock of packaging materials equivalent to one month of projected sales.

# 2. Formulation & Product Quality

## Risk: Instability of Chemical-Free Ingredients

Natural, chemical-free skincare products lack harsh synthetic preservatives, which can sometimes lead to a shorter shelf life, product separation, or spoilage if exposed to extreme temperatures during shipping.

### Mitigation:

Conduct rigorous stress testing (temperature and time) during R&D. Utilize natural, plant-derived preservatives (like Vitamin E or Rosemary Extract). Clearly communicate the 'best by' date to customers to manage expectations.

# 3. Marketing & Market Reception

## Risk: Low Engagement in the Men's Campaign

Targeting men to break the skincare stigma is a core strategy, but the messaging might miss the mark, resulting in low conversion rates and wasted ad spend on platforms like TikTok.

### Mitigation:

Implement A/B testing on ad sets to determine which messaging resonates best. Start with a smaller ad budget and scale up based on performance data. Partner with relatable male micro-influencers to build authentic trust rather than relying solely on brand-directed ads.

# 4. Technical & Operational

## Risk: E-commerce Platform Downtime During Launch

High traffic volumes during the initial campaign launch could crash the website, preventing users from purchasing the 10-minute routine kit.

### Mitigation:

Ensure the hosting provider guarantees scalable bandwidth. Conduct load testing on the e-commerce platform prior to Phase 6 (Official Launch). Have the IT/Ops team on standby during the first 48 hours of the launch.