## Project Plan - Gantt
TerraGlow Project Timeline |  |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Task ID | Phase / Task Name | Assignee | Status | Duration (Wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
1.0 | Phase 1: Research & Formulation |  |  | 4
1.1 | Market & Competitor Analysis (Business Frameworks) | Strategy | Not Started | 2 | bar: Month 1 W1 to Month 1 W2
1.2 | Formulate Chemical-Free Skincare Line | R&D | Not Started | 3 | bar: Month 1 W2 to Month 1 W4
2.0 | Phase 2: Packaging & Sustainability |  |  | 4
2.1 | Source 100% Recyclable Packaging | Operations | Not Started | 2 | bar: Month 2 W5 to Month 2 W6
2.2 | Zero-Waste Compliance Testing | QA Team | Not Started | 2 | bar: Month 2 W7 to Month 2 W8
3.0 | Phase 3: Brand Identity & Guide |  |  | 4
3.1 | Design TerraGlow Brand Assets (Canva/Adobe) | Design | Not Started | 3 | bar: Month 3 W9 to Month 3 W11
3.2 | Draft 10-Minute Routine Beginner's Guide | Content | Not Started | 2 | bar: Month 3 W11 to Month 3 W12
4.0 | Phase 4: Digital Presence & Operations |  |  | 4
4.1 | Develop E-Commerce Platform | Web Dev | Not Started | 3 | bar: Month 4 W13 to Month 4 W15
4.2 | Database Setup for Inventory & Customer Mgmt | IT / Ops | Not Started | 2 | bar: Month 4 W15 to Month 4 W16
5.0 | Phase 5: Marketing & Campaign Design |  |  | 4
5.1 | Generate TikTok Marketing Content | Marketing | Not Started | 2 | bar: Month 5 W17 to Month 5 W18
5.2 | Configure Audience Targeting & Ad Sets (Men's Segment) | Performance Mktg | Not Started | 3 | bar: Month 5 W18 to Month 5 W20
6.0 | Phase 6: Official Launch |  |  | 4
6.1 | Finalize Risk Mitigation & Logistics | Project Mgr | Not Started | 2 | bar: Month 6 W21 to Month 6 W22
6.2 | Go-Live Activation & KPI Tracking | All Teams | Not Started | 2 | bar: Month 6 W23 to Month 6 W24